## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | sumayya | 2026-01-06 | Ticket category misclassification for short inputs | Sprint 1 | sumayya | Functional | Retrained classification model with additional short-text samples | 2026-01-09 | Closed | Accuracy improved after retraining
2 | ranjitha | 2026-01-07 | NER failing to extract usernames with special characters | Sprint 1 | ranjitha | Functional | Updated regex patterns and retrained NER model | 2026-01-10 | Closed | Entity extraction working correctly
3 | soundarya | 2026-01-05 | API returning 500 error for empty request body | Sprint 1 | soundarya | Backend | Added input validation and error handling middleware | 2026-01-07 | Closed | Now returns proper 400 error
4 | rishika | 2026-01-08 | Incorrect priority assigned for urgent keywords | Sprint 1 | rishika | Logic | Updated rule-based priority conditions | 2026-01-11 | Closed | Priority logic validated
5 | tejdeep | 2026-01-08 | Frontend not displaying generated ticket preview | Sprint 1 | tejdeep | UI | Fixed JSON response mapping in frontend component | 2026-01-08 | Closed | UI rendering issue resolved
6 | shekhar | 2026-01-09 | Slow response time during model prediction | Sprint 1 | shekhar | Performance | Optimized model loading and reduced unnecessary computations | 2026-01-11 | Closed | Response time reduced
7 | pranitha | 2026-01-05 | Dataset upload failure due to encoding issue | Sprint 1 | pranitha | Data | Converted dataset to UTF-8 encoding | 2026-01-06 | Closed | Data loads successfully
8 | praveen | 2026-01-10 | Cross-Origin request blocked during integration | Sprint 1 | praveen | Integration | Updated CORS configuration in backend server | 2026-01-10 | Closed | Frontend-backend integration successful

## Sheet2
Logical
User Interface
Maintainability
Standards
Others